| ### Building-Level Technology and Learning Implementation Plan – 3 Year |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of School: Coulee City School |  |  |  |  |  |  | Grades (Example: Elem / MS / HS): Elem/MS |  |  |  |
| School Improvement Goal (taken from your building’s School Improvement Plan): Students at Coulee City School will continue to improve their performance on all WASL tests. Objective: No later than 2014, all students in grades five and eight will meet the minimum WASL standards on the science tests. |  |  |  |  |  |  |  |  |  |  |
| Technology and Learning Strategy: To use technology effectively for investigative learning in science. |  |  |  |  |  |  |  |  |  |  |
| Rationale (Research): Research shows a strong positive impact on test scores as a result of using a kit-based, hands on, investigative science curriculum over several years. It is also suggested that changes in teachers’ instructional practices from traditional text-book curriculum to more hands on, collaborative, and constructivist approaches are a catalyst for higher student performance on tests. This transition will require more professional development to implement inquiry-oriented instruction. |  |  |  |  |  |  |  |  |  |  |
| School Year | Activity |  |  | Person(s) Responsible | Hardware (HW), Software (SW), & Tech Support (TS) Needs | Professional Development (PD) Needs | Purchase / Budget / Potential Funding Source(s) |  |  | Evaluation Strategies and/or Tools |
|  | What actions will occur? What steps will staff take to achieve this goal? |  |  | Who will provide leadership? Who will do the work to make sure that this activity occurs? | What HW, SW and TS is needed to reach this goal? Include quantities and distribution. | What professional development does the staff need in order to take the steps to achieve this goal? | What is the cost of the additional HW, SW, TS and PD needed to reach this goal? What are the possible funding sources? Include building and district sources, as well as grants. |  |  | How will you evaluate the implementation of this strategy? What tool(s) will you use? |
| Year 1: 2004-2005 | Incorporate the use of FOSS Kit curriculum in grades K-8 |  |  | Principal |  | Professional development on implementing the FOSS Model | Trainer/Consultant - $500 from REAP/SRSAP |  |  | Princ. Observation LoTi tool |
|  | Use technology that supports the FOSS model |  |  | Building Technology Coordinator | Access to computer lab, internet connection, software for content areas | Training on using FOSSWEB and CDROM | Software – FOSS CD ROM Lab Pack - $500 from Building Budget. Training – Technology Coordinator (part of job duties) from Building Budget |  |  | Princ. Observation PILOT tool |
| Year 2: 2005-2006 | Continue to incorporate the use of FOSS Kit curriculum in grades K-8 |  |  | Principal |  |  |  |  |  | Princ. Observation LoTi tool |
|  | Use technology that supports the FOSS model |  |  | Building Technology Coordinator | Projectors for classroom for teacher demonstration | Using projectors in the classroom | 2 LCD projectors - $1100.00 each from REAP/SRSAP Training – Technology Coordinator (part of job duties) from Building Budget |  |  | Princ. Observation PILOT tool |
| Year 3: 2006-2007 | Continue to incorporate the use of the FOSS Kit curriculum in grades K-8 |  |  | Principal |  |  |  |  |  | Princ. Observation LoTi tool |
|  | Use technology that supports the FOSS model |  |  | Building Technology Coordinator | Document Cameras for teacher demonstration | Using Document Cameras in the classroom | 3 Document Cameras - $750.00 each from REAP/SRSAP Training – Technology Coordinator (part of job duties) from Building Budget |  |  | Princ. Observation PILOT tool |
| SIP Team Leader Completing This Form |  |  | ## Kelley Schafer |  |  |  |  | # Completion Date | 3/1/04 |  |
| Other SIP Team Participants |  | Brandon Walsh (Grade 6-8), Tami Spurbeck (Grade 4), Barb Thiry (Grade 1), Ed Fisk (Principal) |  |  |  |  |  |  |  |  |