# ACTION PLAN – Curriculum & Academic Achievement

GOAL:  Students at Coulee City School will continue to improve their performance on all WASL tests.

OBJECTIVE:  No later than 2014, all students in grades 4 and 7 will meet the minimum WASL standards on the reading tests.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| We will align our reading curriculum with the state EALRs. | On going: Reading will be the primary curriculum focus in 2005-06 | Principal; Teachers | Washington State EALRs Example Curriculum guides from other districts | A reading curriculum for each grade level that is easily understood by parents and teachers, is aligned with the EALRs, and provides continuity from grade level to grade level. | To be determined; 2006 will be the adoption year for new books, supplies and materials |
| Teachers will develop reading documents by grade level | On going | Teachers | Reading Frameworks (OSPI) | Same as above | Same as above |
| Teachers will visit other districts to observe and study successful reading programs | To be scheduled during 2003-04 school year. | Teachers | Transportation | Teachers will become more familiar with successful programs being used in other schools | Minimal – Some transportation costs |

ACTION PLAN – Curriculum & Academic Achievement

GOAL:  Students at Coulee City School will continue to improve their performance on all WASL tests.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Teachers attended an in-service with Jill Bowman, a writing specialist | Fall 2002 – 10/11/02 | Teachers K-5 | Posters of 6 traits Books to model and teach models of each trait | Teachers will learn practical ideas that will enable them to help their students become better writers | Cost for this program was built into the 2002-03 budget; funds came from I-728 budget |
| Teachers will visit schools that have a writing curriculum in place 6 + 1 trait in action | To be scheduled during the 2003-04 school year | Teachers | Substitute teachers | Teachers will see how writing is taught in other schools; they will gain knowledge to help choose practices and resources that will work best with our students | Minimal – some transportation costs |
| Align our curriculum with the EALRs | To be completed by fall 2005 | Principal and teachers | WA State EALRs | A writing curriculum for each grade level that is easily understood by parents and teachers, is aligned with the EALRs, and provides continuity from grade level to grade level |  |
| Look at different writing programs | Ongoing | Teachers/Curriculum committee | To be determined: Based on visits and research | Information used to develop curriculum | To be determined |

OBJECTIVE:  No later than 2014, all students in grades four and seven will meet the minimum WASL standards on the writing tests.

# ACTION PLAN – Curriculum & Academic Achievement

GOAL:  Students at Coulee City School will continue to improve their performance on all WASL tests.

OBJECTIVE:  No later than 2014, all students in grades 4 and 7 will meet the minimum WASL standards on the math tests.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Two teachers will participate in No-Limit Grant through ESD 171 | August 2003 – May 2004 | Sean Matthewson Kelley Schafer | Substitute time for nine training days for each teacher | Improve math scores on WASL test through improved instructional practices | $200.00 for training and $7,000.00 for equipment |
| Continue to use Saxon math (K-5) and Glencoe math (6-8) and update editions as needed | Continuing | K-8 Staff | To be determined each year | Continue maintenance of students’ basic skills | To be determined each year. Will depend on need for updated materials |
| Supplement math instruction with constructivist approach | Continuing | K-8 Staff | Possible in-service on constructavist methods Resources (i.e. visual math, problem solving, math receipts) | Increase students’ ability to problem solve, communicate mathematically and write in math | To be determined: will depend upon need for materials and training |

# ACTION PLAN – Curriculum & Academic Achievement

GOAL:  Students at Coulee City School will continue to improve their performance on all WASL tests.

OBJECTIVE:  No later than 2014 all students in grades five and eight will meet the minimum WASL standards on the science test.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| We will align our science curriculum with the state EALRs | On going: Science will be the primary focus 2003-04 | Principal, Teachers | Washington State EALRs Sample curriculum guides from other districts | A science curriculum for each grade level that is easily understood by parents and teachers, is aligned with the EALRs and provides continuity from grade level to grade level | To be determined; we anticipate submitting budget needs to the superintendent and board in the spring of 2004 |
| Science teachers will review science curriculum and science kits that might be appropriate for our school | Review and study during 2003-04 school year. Implement new curriculum in fall of 2004 | Principal, Teachers Jack Horne from the ESD will demonstrate science kits | Sample curriculum materials; sample science kits | Same as above | Same as above |
| Teachers will visit other districts to observe and study successful science programs | To be scheduled ASAP | Teachers; Principal | Transportation | Teachers will become more familiar with successful programs being used in other schools | Minimal – some transportation costs |
| Adopt new science curriculum, books or kits or other instructional programs | By spring of 2004 to allow superintendent and board to consider requests during budget adoption | Science teachers | Resources recommended by science teachers from activity above | Same as above | Same as above |

ACTION PLAN – Curriculum and Academic Achievement

GOAL:  Students at Coulee City School will continue to improve their performance on all WASL tests

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| We will align our social studies curriculum with the state EALRs | On going: Currently a framework for the Middle School is being built The school year 2004-05 is scheduled to be the year we will focus upon social studies | Principal, Teachers | WA State EALRs Curriculum guides and examples of what other districts are doing | A framework for each grade level will be built so that there will be continuity from grades K-8 | To be determined |
| Social Studies in all grades will be targeted toward the interests/experience/ background of students. Teachers will learn effective ways to tie history and social studies to student’s lives today | On going: same as above We need to plan for a K-5 curriculum adoption in 2004-05 | Teachers | In-services programs - by learning how to present questions, social studies teachers can become more effective teachers of the subject | Student will realize that social studies relates to them personally. By making this connection they will take more interest in history/social studies, and they will learn more because the subject has relevance to them | To be determined when the Social Studies becomes a target area for curriculum review and adoption (2004-05) |

OBJECTIVE:  No later than 2014, all students in grades four and seven will meet the minimum WASL standard on the social studies tests

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Fall open house | The open house will be held as early in the school year as possible preferably during the first three weeks of school | Principal and teachers | None | Teachers will explain course/class expectations to parents | None |
| Student/Parent Conferences | Student/Parent conferences are scheduled in the fall and again in the spring each school year | Conference days will be scheduled by the calendar committee; conference times will be scheduled by the teachers or in the school office | None | Students will explain what they have learned; teachers will explain students’ progress to parents | None |
| Weekly progress reports (middle school level) and folders (elementary level) | Weekly | Teachers | None that are not currently available | Parents will be provided with weekly assessments of their child’s progress; Parents will be able to communicate with the teachers and take action if necessary, before problems become serious | None |
| Phone calls, visits, notes, a letter home, special conferences | As needed | Teacher (although some are initiated by parents) | Same as above | Parents will be kept informed of their child’s progress. If change or corrective actions are needed, parents and teacher can collaborate | None |

# ACTION PLAN – Communications

GOAL:  The school will improve communications with parents

OBJECTIVE:  Teachers will continue to communicate each child’s progress to parents at least four times through the school year.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| A suggestion box will be available for parents to offer suggestions and concerns | Fall open house | Principal | Suggestion box, paper, pencils | We will become aware of concerns and issues parents want us to consider | None |
| Parents are encouraged to send us email messages, notes or phone calls | On going | Principal will encourage this activity at the open house, in the building newsletters and through any other options that become available | Nothing more than the normal school supplies and communications tools | Same as above | None |

ACTION PLAN – Communications

GOAL:  The school will improve communications with parents

OBJECTIVE:  At the beginning of each school year, parents will be given an opportunity to communicate suggestions

for concerns for the coming year.

# ACTION PLAN – Communications

GOAL:  The school will improve communications with parents

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Teachers will prepare written grade level expectations that can be given to students (as appropriate) and parents | The information will be prepared at the start of each school year | Teachers will write the expectations; the principal will keep a copy on file | None | Parents and students will know what is required for students to be successful in each class | No additional budget needed |

OBJECTIVE:  At the beginning of each year, teachers will explain the grade level expectations to parents at the fall open house

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Teachers will meet as a building faculty or in teams to discuss curriculum issues and concerns | At the beginning of the school year, preferably before the first day of school | Principal, Teachers | Time | The curriculum at each grade level in the school will be easily understood by parents and teachers, will be aligned with the EALRs and will provide continuity from grade level to grade level | None if the meeting time is included in the board approved calendar as part of the teachers scheduled work year |
| Teachers will meet once each quarter to discuss curriculum issues and concerns | Quarterly meetings will be scheduled | Principal, Teachers | Time | Same as above | Same as above |

ACTION PLAN – Professional Development & Planning

GOAL:  Teachers will meet regularly to discuss curriculum issues

OBJECTIVE:  Teachers will meet at the beginning of each school year and at least quarterly each year

to discuss curriculum issues and concerns.

| Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| Three half-days for staff development and/or SIP planning/ implementation will be added to the district calendar | The days must be agreed upon by the Teachers Association and the Administration and then approved by the Superintendent and the Board of Directors | Board of Directors, Administration, Teachers | None | Teachers will have time to collaborate on curriculum and instructional planning issues. The focus will be upon strategies to help students be more successful on the WASL tests | If students are released early, none If these days are scheduled in addition to the days in the calendar approved by the Board of Directors in the Spring of 2003, there will be the cost of 1/2 day’s pay for each teacher for each half-day added. |

# ACTION PLAN – Professional Development & Planning

GOAL:  Time for professional development and district staff collaboration will be increased.

OBJECTIVE:  In the 2003-04 school year, up to three half-days for staff development and for SIP planning/implementation

will be added to the district calendar.

# ACTION PLAN – Bullying/Intimidation & Harassment

GOAL:  Incidents of bullying/intimidation and harassment at school will be reduced.

OBJECTIVE: In the spring of 2004 a bullying survey will be given to students in grades 3 – 8.

- At least 75% of the students will respond/report that they would report a witnessed incident of

physical aggression to a teacher or their adult at school.

| B. Less than 15% of the girls in 6th to 8th grades will report that they feel victimized by peers once a month or more often. Action/Activity | Timeline | Responsibility | Resources Needed | Outcome | Budget |
| --- | --- | --- | --- | --- | --- |
| A bullying/intimidation and harassment survey will be given to all students in grades 3 – 8 in April or May, 2004 | April or May, 2004 | Principal & Counselor | Survey – to be developed with the help of WSU | We will be able to compare 2003 results with 2004 results | Cost will be minimal. In 2003, WSU did not charge us for the survey |
| A program to combat bullying/intimidation and harassment will be presented to all students - grades 4 - 8 | September/ October, 2003 and on going | Counselor | Using the same survey we used in 2003 may be an option. WSU has agreed to assist. We do not know if they will use the same survey | Intent will be to reduce the incidents of bullying/ intimidation and harassment | $50.00 for a video |
| An in-service program concerning bullying/intimidation and harassment will be presented to the faculty | November, 2003 | Principal | Bullying power point provided by OSPI | Teachers will be better prepared to recognize and prevent bullying/ intimidation and harassment | No cost |
| Counselor will meet with individual students and groups when/if incidents of bullying/intimidation and harassment are reported | On-going | Counselor | None | Inform students about inappropriate behavior and bring about change; reduce incidents of bullying/ intimidation and harassment | No additional costs |